## Weekly Plan
Week | Date Range | Phase | Topics / Skills | Mini Project Task | Repo Folder(s) | Resources (links) | Progress (☐/☑)
1 | 2025-10-25 → 2025-10-31 | Phase 1 – Core Java, Git, DSA basics | Java syntax fundamentals: variables, primitive types, operators, Scanner input; if/else, switch, loops (for/while). Git basics: init repo, commit, push. | CLI 'Hello PixelLife' menu with options (New Game, Load, Quit). Read user input and print different text. | /scripts/Week01_ConsoleMenu.java /README.md (Getting Started) | Java Basics (Oracle): https://docs.oracle.com/javase/tutorial/java/nutsandbolts/index.html Git branches/feature workflow: https://www.atlassian.com/git/tutorials/using-branches | ☐
2 | 2025-11-01 → 2025-11-07 | Phase 1 – Core Java, Git, DSA basics | Methods & parameters; return values; arrays; try/catch basics; code style & naming. Continue practicing Git commits. | Console inventory prototype: store starter items in an array/list, print them in a table. | /scripts/Week02_InventoryConsole.java /data/items_sample.txt | Java Basics (Oracle): https://docs.oracle.com/javase/tutorial/java/nutsandbolts/index.html Git branches/feature workflow: https://www.atlassian.com/git/tutorials/using-branches | ☐
3 | 2025-11-08 → 2025-11-14 | Phase 1 – Core Java, Git, DSA basics | OOP intro: classes, objects, fields, constructors, getters/setters, encapsulation. | Create Player class (hp, energy, gold). Implement savePlayer() that writes stats to a file (JSON/text). | /scripts/player/Player.java /data/save_slot1.json | Java OOP Concepts: https://docs.oracle.com/javase/tutorial/java/concepts Java Basics (Oracle): https://docs.oracle.com/javase/tutorial/java/nutsandbolts/index.html | ☐
4 | 2025-11-15 → 2025-11-21 | Phase 1 – Core Java, Git, DSA basics | Inheritance, interfaces, polymorphism; packages & access modifiers; clean code & Single Responsibility; intro to Gradle project layout. | Enemy subclasses (Slime, Bat) that share an interface EnemyBehavior. Turn-based combat simulator in console. | /scripts/combat/ /tests/combat_tests/ (build Gradle skeleton) | Java OOP Concepts: https://docs.oracle.com/javase/tutorial/java/concepts Game Programming Patterns: https://gameprogrammingpatterns.com/ | ☐
5 | 2025-11-22 → 2025-11-28 | Phase 1 – Core Java, Git, DSA basics | Java Collections (ArrayList, HashMap); generics; exceptions deeper. Big-O thinking: array vs list; stack/queue; why HashMap is fast. | Inventory system using ArrayList<Item> + HashMap<String,Integer> for quantities; add/drop items; save to JSON. | /scripts/inventory/ /data/items.json | Java Basics (Oracle): https://docs.oracle.com/javase/tutorial/java/nutsandbolts/index.html Java OOP Concepts: https://docs.oracle.com/javase/tutorial/java/concepts | ☐
6 | 2025-11-29 → 2025-12-05 | Phase 1 – Core Java, Git, DSA basics | Algorithms on collections: sorting by price, searching by name; intro to JUnit tests; Git feature branches & pull requests. | Shop system: buy/sell items sorted by price. Write JUnit tests for buy/sell logic. Work in a new Git feature branch then merge. | /scripts/shop/ /tests/shop_tests/ .git (feature branches) | Feature Branch Workflow: https://www.atlassian.com/git/tutorials/comparing-workflows/feature-branch-workflow Git branches/feature workflow: https://www.atlassian.com/git/tutorials/using-branches | ☐
7 | 2025-12-06 → 2025-12-12 | Phase 1 – Core Java, Git, DSA basics | Game math 2D: coordinates (x,y), vectors, movement step; concept of delta time; game loop theory (update → render). | Console grid world: move player with WASD on 2D map; print map each frame in console. | /scripts/movement_grid/ | Game Programming Patterns: https://gameprogrammingpatterns.com/ (Game Loop chapter) | ☐
8 | 2025-12-13 → 2025-12-19 | Phase 2 – 2D Game Basics w/ LibGDX | Set up LibGDX project with Gradle (gdx-liftoff); import into IDE; render window; SpriteBatch; keyboard input. | First LibGDX scene 'demo_movement': draw player sprite and move with arrow keys. | /scenes/demo_movement/ /assets/player.png (core module src) | LibGDX Setup: https://libgdx.com/wiki/start/setup LibGDX Project Generation: https://libgdx.com/wiki/start/project-generation Import & Run LibGDX Project: https://libgdx.com/wiki/start/import-and-running LibGDX Wiki: https://libgdx.com/wiki/ | ☐
9 | 2025-12-20 → 2025-12-26 | Phase 2 – 2D Game Basics w/ LibGDX | Sprites & animations: TextureRegion, Animation class, frame timing; organize sprite sheets. | Idle/walk animation for Player; switch animation based on movement. | /assets/sprites/player/ /scripts/player/PlayerAnimation.java | LibGDX Wiki: https://libgdx.com/wiki/ | ☐
10 | 2025-12-27 → 2026-01-02 | Phase 2 – 2D Game Basics w/ LibGDX | Tilemaps: build a small map in Tiled; load tilemap in LibGDX; basic collision boxes (AABB). | Overworld tilemap with walls. Stop player when colliding. | /assets/tilesets/ /scenes/overworld/ /scripts/collision/ | LibGDX Wiki: https://libgdx.com/wiki/ | ☐
11 | 2026-01-03 → 2026-01-09 | Phase 2 – 2D Game Basics w/ LibGDX | Finite State Machines (FSM) for Player (idle/walk/attack); enums & switch; cooldown timers. | Implement PlayerState enum and update() method that handles movement/attack. | /scripts/player/state/ | Java OOP Concepts: https://docs.oracle.com/javase/tutorial/java/concepts Game Programming Patterns: https://gameprogrammingpatterns.com/ (State pattern) | ☐
12 | 2026-01-10 → 2026-01-16 | Phase 2 – 2D Game Basics w/ LibGDX | UI/HUD with Scene2D UI: health/stamina bars, text labels; BitmapFont; pause menu. | HUD overlay showing HP/energy; pause/resume menu. | /scenes/ui/hud/ /assets/fonts/ /scripts/ui/Hud.java | Scene2D UI: https://libgdx.com/wiki/graphics/2d/scene2d/scene2d-ui | ☐
13 | 2026-01-17 → 2026-01-23 | Phase 2 – 2D Game Basics w/ LibGDX | Basic enemy AI: patrol route, chase player when in range; timers and cooldowns. | Slime enemy that wanders and then chases the player. | /scripts/enemies/slime/ /assets/enemies/slime.png | LibGDX Wiki: https://libgdx.com/wiki/ | ☐
14 | 2026-01-24 → 2026-01-30 | Phase 2 – 2D Game Basics w/ LibGDX | Real-time combat: attack hitbox, damage calc, knockback. Show floating damage numbers. | Player can attack slime, slime loses HP, numbers pop above slime. | /scripts/combat_rt/ /assets/effects/damage_numbers/ | LibGDX Wiki: https://libgdx.com/wiki/ | ☐
15 | 2026-01-31 → 2026-02-06 | Phase 2 – 2D Game Basics w/ LibGDX | Audio: background music loop, SFX (sword swing, footsteps); AssetManager for loading. | Add music + SFX; settings for volume. | /assets/audio/ /scripts/audio/ | LibGDX Wiki: https://libgdx.com/wiki/ | ☐
16 | 2026-02-07 → 2026-02-13 | Phase 2 – 2D Game Basics w/ LibGDX | Saving/loading world state (player pos, HP, inventory); build runnable desktop JAR; attempt Android build. | Vertical Slice 1: walk around map, fight slime, pick loot, HUD works, can Save/Load. | /saves/ /data/savegame.json /builds/ | Import & Run LibGDX Project: https://libgdx.com/wiki/start/import-and-running LibGDX multiplatform targets: https://github.com/libgdx/libgdx | ☐
17 | 2026-02-14 → 2026-02-20 | Phase 3 – Game Systems & Data Structures | Graphs/grids for navigation; Breadth-First Search (BFS) pathfinding; review Big-O for BFS. | Create BFSPathfinder that finds route around obstacles on tile grid. | /scripts/pathfinding/BFSPathfinder.java | A* Pathfinding (Red Blob Games): https://www.redblobgames.com/pathfinding/a-star/introduction.html | ☐
18 | 2026-02-21 → 2026-02-27 | Phase 3 – Game Systems & Data Structures | A* pathfinding for smarter enemy movement; heuristic costs. | Enemy uses A* to navigate around walls, not just straight line. | /scripts/pathfinding/AStarPathfinder.java | A* Pathfinding (Red Blob Games): https://www.redblobgames.com/pathfinding/a-star/introduction.html | ☐
19 | 2026-02-28 → 2026-03-06 | Phase 3 – Game Systems & Data Structures | Entity-Component-System (ECS) architecture: Components (Position, Velocity, Renderable), Systems (MovementSystem, RenderSystem). Decouple logic using components, not giant classes. | Refactor Player + Slime into ECS components/systems. | /scripts/ecs/ /scripts/systems/ | Game Programming Patterns: https://gameprogrammingpatterns.com/ (Component pattern) | ☐
20 | 2026-03-07 → 2026-03-13 | Phase 3 – Game Systems & Data Structures | Robust save/load: serialization to JSON/Kryo; autosave slots; load menu UI. | Save slots menu + autosave every N seconds. | /saves/ /scripts/save/ /scenes/ui/save_menu/ | LibGDX Wiki: https://libgdx.com/wiki/ | ☐
21 | 2026-03-14 → 2026-03-20 | Phase 3 – Game Systems & Data Structures | Inventory UI drag/drop (Scene2D); crafting basics (combine 2 items -> new item). Collections & HashMap practice. | Drag item from backpack to hotbar, craft simple potion. | /scripts/inventory_ui/ /assets/items/ | Scene2D UI: https://libgdx.com/wiki/graphics/2d/scene2d/scene2d-ui | ☐
22 | 2026-03-21 → 2026-03-27 | Phase 3 – Game Systems & Data Structures | Dialogue + Quest system: text box with typewriter effect; basic fetch quest tracked in QuestLog. | NPC dialog window + quest journal (collect 3 herbs). | /scripts/dialogue/ /scripts/quest/ /data/dialogue.json | LibGDX Wiki: https://libgdx.com/wiki/ | ☐
23 | 2026-03-28 → 2026-04-03 | Phase 3 – Game Systems & Data Structures | 2D physics/platforming: gravity, jump arc, continuous collision detection; optional Box2D intro. | Platformer test scene with jump + collision vs ground/enemy. | /scenes/platformer_test/ /scripts/physics2d/ | LibGDX Wiki: https://libgdx.com/wiki/ | ☐
24 | 2026-04-04 → 2026-04-10 | Phase 3 – Game Systems & Data Structures | Performance basics: measure delta time & FPS; avoid garbage allocations; object pooling. Code cleanup sprint. | FPS debug overlay showing FPS, ms/frame, memory usage. | /scripts/debug/FPSOverlay.java | LibGDX Wiki: https://libgdx.com/wiki/ ParticleEffects: https://libgdx.com/wiki/graphics/2d/2d-particleeffects | ☐
25 | 2026-04-11 → 2026-04-17 | Phase 4 – Advanced Gameplay & Tools | Camera systems: OrthographicCamera follow player smoothly (lerp), camera shake on hit, parallax background. | CameraFollow class that centers camera on player + small shake when damaged. | /scripts/camera/CameraFollow.java | Orthographic Camera: https://libgdx.com/wiki/graphics/2d/orthographic-camera | ☐
26 | 2026-04-18 → 2026-04-24 | Phase 4 – Advanced Gameplay & Tools | Lighting & day/night cycle; simple shader / color tint overlay for night; intro to render pipeline. | Day/night tint overlay + lantern light around player. | /scripts/lighting/ /assets/shaders/ | LibGDX Wiki: https://libgdx.com/wiki/ | ☐
27 | 2026-04-25 → 2026-05-01 | Phase 4 – Advanced Gameplay & Tools | Particle effects (dust, hit sparks) and object pooling for performance. | Spawn hit spark particle when player attacks; dust puff when walking. | /assets/particles/ /scripts/effects/ | ParticleEffects: https://libgdx.com/wiki/graphics/2d/2d-particleeffects | ☐
28 | 2026-05-02 → 2026-05-08 | Phase 4 – Advanced Gameplay & Tools | Menus/settings/options screen: key bindings, volume sliders, language toggle; write to settings.json. | Settings menu UI that edits /data/settings.json and applies changes live. | /scenes/ui/settings/ /data/settings.json /scripts/ui/SettingsMenu.java | Scene2D UI: https://libgdx.com/wiki/graphics/2d/scene2d/scene2d-ui | ☐
29 | 2026-05-09 → 2026-05-15 | Phase 4 – Advanced Gameplay & Tools | Build pipeline: Gradle tasks, automated builds; Git feature branches, pull requests, code review; GitHub Actions CI to run tests/build. | Add .github/workflows/build.yml to auto-build + run tests on push. | /.github/workflows/build.yml /tests/ | Feature Branch Workflow: https://www.atlassian.com/git/tutorials/comparing-workflows/feature-branch-workflow Git branches/feature workflow: https://www.atlassian.com/git/tutorials/using-branches | ☐
30 | 2026-05-16 → 2026-05-22 | Phase 4 – Advanced Gameplay & Tools | Game Programming Patterns: Event/Observer bus, Command, State, Singleton vs Dependency Injection. Decouple gameplay code. | Global EventBus for PlayerHit, ItemCollected; Command pattern for player actions. | /scripts/core/events/ /scripts/core/commands/ | Game Programming Patterns: https://gameprogrammingpatterns.com/ | ☐
31 | 2026-05-23 → 2026-05-29 | Phase 4 – Advanced Gameplay & Tools | Localization & text externalization; resource bundles / JSON; language menu (EN/VI). | Add en.json & vi.json, option in Settings to switch language. | /data/lang/en.json /data/lang/vi.json /scripts/i18n/ | Scene2D UI: https://libgdx.com/wiki/graphics/2d/scene2d/scene2d-ui | ☐
32 | 2026-05-30 → 2026-06-05 | Phase 4 – Advanced Gameplay & Tools | Accessibility & UX polish: readable fonts, color contrast, input remapping, autosave indicator. Bug-fix sprint and playtest. | QA checklist markdown: list bugs, usability issues, FPS problems for next milestone. | /docs/QA_checklist.md | Game Programming Patterns: https://gameprogrammingpatterns.com/ | ☐
33 | 2026-06-06 → 2026-06-12 | Phase 5 – Engine, Optimization & Platform | Networking basics in Java (sockets / KryoNet-style); sync player position between two clients for local co-op. | Prototype LAN sync server/client sending player x,y. | /scripts/net/Server.java /scripts/net/Client.java | Java Basics (Oracle): https://docs.oracle.com/javase/tutorial/java/nutsandbolts/index.html LibGDX Wiki: https://libgdx.com/wiki/ | ☐
34 | 2026-06-13 → 2026-06-19 | Phase 5 – Engine, Optimization & Platform | Advanced AI: Behavior Trees and gdx-ai library; enemy boss logic (patrol → chase → attack → flee). | BossBehaviorTree using gdx-ai BehaviorTree API. | /scripts/ai/behavior_tree/ /data/ai/boss.bt | gdx-ai (behavior trees): https://github.com/libgdx/gdx-ai | ☐
35 | 2026-06-20 → 2026-06-26 | Phase 5 – Engine, Optimization & Platform | Quest / progression system advanced: multi-step quests, rewards, gating new map areas; persistent quest log in save file. | Quest chain across 3 NPCs, unlocks new zone. | /scripts/quest/ /data/quests.json | LibGDX Wiki: https://libgdx.com/wiki/ | ☐
36 | 2026-06-27 → 2026-07-03 | Phase 5 – Engine, Optimization & Platform | Tooling & level design pipeline: Tiled maps, spawn tables, LevelLoader that spawns ECS entities from map data. | LevelLoader utility + overworld_v2 scene using new loader. | /scripts/level_loader/ /scenes/overworld_v2/ | LibGDX Wiki: https://libgdx.com/wiki/ | ☐
37 | 2026-07-04 → 2026-07-10 | Phase 5 – Engine, Optimization & Platform | Profiling & optimization deep dive: heap allocation tracking, object pooling, frame time budgets; performance HUD. | ProfilerOverlay showing FPS, ms/frame, heap usage on-screen. | /scripts/debug/ProfilerOverlay.java | LibGDX Wiki: https://libgdx.com/wiki/ | ☐
38 | 2026-07-11 → 2026-07-17 | Phase 5 – Engine, Optimization & Platform | Platform builds & input: Android touch controls (virtual joystick/buttons), UI scaling for mobile; generate Android APK. | Mobile demo scene with virtual joystick and attack button; run on Android device. | /scripts/input/mobile/ /scenes/mobile_demo/ /builds/ | LibGDX multiplatform targets: https://github.com/libgdx/libgdx | ☐
39 | 2026-07-18 → 2026-07-24 | Phase 5 – Engine, Optimization & Platform | Telemetry / analytics basics: log playtime, deaths, items collected to a local file for balancing. | TelemetryLogger that appends session stats to telemetry.log. | /scripts/telemetry/ /saves/telemetry.log | Java Basics (Oracle): https://docs.oracle.com/javase/tutorial/java/nutsandbolts/index.html | ☐
40 | 2026-07-25 → 2026-07-31 | Phase 5 – Engine, Optimization & Platform | Architecture cleanup: package by feature (com.pixelife.core, .ai, .ui, .net); dependency boundaries; prep Alpha build. | Refactor packages + update README architecture section. | /scripts/* (refactored) /README.md | Game Programming Patterns: https://gameprogrammingpatterns.com/ | ☐
41 | 2026-08-01 → 2026-08-07 | Phase 6 – Polish, Portfolio & Job Prep | Documentation & technical writing: JavaDoc comments; architecture diagrams; README 'How to Build/Run'; create /docs. | Write /docs/architecture.md explaining ECS, systems, save/load. | /docs/ /README.md | Game Programming Patterns: https://gameprogrammingpatterns.com/ | ☐
42 | 2026-08-08 → 2026-08-14 | Phase 6 – Polish, Portfolio & Job Prep | Portfolio assets: screenshots, GIFs, gameplay trailer; draft itch.io store page & devlog. | Capture gameplay video + screenshots and store in assets/marketing; write itchio_page.md. | /assets/marketing/ /docs/itchio_page.md | LibGDX multiplatform targets: https://github.com/libgdx/libgdx | ☐
43 | 2026-08-15 → 2026-08-21 | Phase 6 – Polish, Portfolio & Job Prep | Resume / LinkedIn / GitHub polish: write CV for 'Gameplay Programmer Intern (Java/LibGDX)'; highlight systems you built. | Draft CV_draft.md summarizing tech stack, projects, GitHub links. | /docs/CV_draft.md | Git branches/feature workflow: https://www.atlassian.com/git/tutorials/using-branches | ☐
44 | 2026-08-22 → 2026-08-28 | Phase 6 – Polish, Portfolio & Job Prep | Interview prep I: Core Java & OOP (memory model, collections, exceptions); explain your engine architecture clearly. | Create interview_core_java.md with Q&A about OOP, collections, game loop, ECS. | /docs/interview_core_java.md | Java OOP Concepts: https://docs.oracle.com/javase/tutorial/java/concepts Java Basics (Oracle): https://docs.oracle.com/javase/tutorial/java/nutsandbolts/index.html | ☐
45 | 2026-08-29 → 2026-09-04 | Phase 6 – Polish, Portfolio & Job Prep | Interview prep II: Data Structures & Algorithms for gameplay: arrays vs lists, hash maps, stacks/queues, BFS/DFS, A* pathfinding. | Implement classic problems in /tests/dsa_practice (stack using array, BFS traversal, etc.) and document complexity. | /tests/dsa_practice/ | A* Pathfinding (Red Blob Games): https://www.redblobgames.com/pathfinding/a-star/introduction.html Java Basics (Oracle): https://docs.oracle.com/javase/tutorial/java/nutsandbolts/index.html | ☐
46 | 2026-09-05 → 2026-09-11 | Phase 6 – Polish, Portfolio & Job Prep | Interview prep III: Game-specific theory: game loop, delta time, collision detection, ECS vs inheritance, physics basics. | Write interview_gameplay.md with explanations + small diagrams. | /docs/interview_gameplay.md | Game Programming Patterns: https://gameprogrammingpatterns.com/ | ☐
47 | 2026-09-12 → 2026-09-18 | Phase 6 – Polish, Portfolio & Job Prep | Team process / soft skills: feature branches, pull requests, code review etiquette, Agile sprint planning, standups. | Write dev_process.md describing how you'll work in a team. | /docs/dev_process.md | Feature Branch Workflow: https://www.atlassian.com/git/tutorials/comparing-workflows/feature-branch-workflow Git branches/feature workflow: https://www.atlassian.com/git/tutorials/using-branches | ☐
48 | 2026-09-19 → 2026-09-25 | Phase 6 – Polish, Portfolio & Job Prep | Release Candidate polish: fix priority bugs, stabilize FPS, memory, crashes. Prepare public demo build + README install steps. | Portfolio Ready Build: export desktop JAR + Android APK and document install in README. | /builds/rc/ /README.md | LibGDX multiplatform targets: https://github.com/libgdx/libgdx Import & Run LibGDX Project: https://libgdx.com/wiki/start/import-and-running | ☐
49 | 2026-09-26 → 2026-10-02 | Phase 7 – Internship Applications & Next Steps | Internship application sprint: research studios, send applications with CV + gameplay trailer + GitHub repo. Track who replies. | applications_tracker.xlsx to log company, contact, status. | /docs/applications_tracker.xlsx (create this spreadsheet manually) | Git branches/feature workflow: https://www.atlassian.com/git/tutorials/using-branches | ☐
50 | 2026-10-03 → 2026-10-09 | Phase 7 – Internship Applications & Next Steps | Collect feedback from playtesters / interviewers; list gaps (math, shaders, networking). Plan fixes and learning goals. | Write feedback_summary.md summarizing feedback and action items. | /docs/feedback_summary.md | Game Programming Patterns: https://gameprogrammingpatterns.com/ | ☐
51 | 2026-10-10 → 2026-10-16 | Phase 7 – Internship Applications & Next Steps | Mock interviews: record yourself answering top 10 Java/OOP/Gameplay questions; review clarity and timing. | mock_interview_notes.md with what went well / needs work. | /docs/mock_interview_notes.md | Java OOP Concepts: https://docs.oracle.com/javase/tutorial/java/concepts A* Pathfinding (Red Blob Games): https://www.redblobgames.com/pathfinding/a-star/introduction.html | ☐
52 | 2026-10-17 → 2026-10-23 | Phase 7 – Internship Applications & Next Steps | Retrospective + next 3 month plan (Unity C#, Unreal C++, shader programming, etc.). Refresh DSA fundamentals weekly. | next_steps_3mo.md: roadmap for next quarter. | /docs/next_steps_3mo.md | Game Programming Patterns: https://gameprogrammingpatterns.com/ A* Pathfinding (Red Blob Games): https://www.redblobgames.com/pathfinding/a-star/introduction.html | ☐

## Milestones
Month | Focus | Deliverable / Milestone | Repo Folders To Update | Progress (☐/☑)
Month 1 (Weeks 1-4) | Core Java syntax, OOP basics, Git workflow. | Text-only PixelLife prototype in console: menu, player stats, simple combat. | /scripts/player/ /scripts/combat/ README.md | ☐
Month 2 (Weeks 5-8) | Collections, basic DSA, grid movement, LibGDX setup. | Player moves in LibGDX window using arrow keys. | /scripts/movement_grid/ /scenes/demo_movement/ /assets/ | ☐
Month 3 (Weeks 9-12) | Animation, tilemap, FSM, HUD/UI. | Walk-around map with animated player + HUD. | /assets/sprites/player/ /scenes/overworld/ /scenes/ui/hud/ | ☐
Month 4 (Weeks 13-16) | Enemy AI basics, combat, audio, save/load. | Vertical Slice 1 (~2-3 min gameplay): fight slime, HUD, Save/Load. | /scripts/enemies/ /scripts/combat_rt/ /saves/ /builds/ | ☐
Month 5 (Weeks 17-20) | Pathfinding (BFS/A*), ECS architecture, save slots. | ECS refactor + smart enemy navigation. | /scripts/pathfinding/ /scripts/ecs/ /scripts/systems/ /scripts/save/ | ☐
Month 6 (Weeks 21-24) | Inventory UI, quests, platforming physics, performance. | Core Gameplay Loop: move, fight, loot, quest, save. | /scripts/inventory_ui/ /scripts/quest/ /scenes/platformer_test/ /scripts/debug/ | ☐
Month 7 (Weeks 25-28) | Camera, lighting, particles, settings menu. | Cinematic feel: camera follow/shake, night cycle, pause/settings. | /scripts/camera/ /scripts/lighting/ /assets/particles/ /scenes/ui/settings/ | ☐
Month 8 (Weeks 29-32) | Build pipeline (CI), patterns/EventBus, localization, UX polish. | Public Demo v0.1 + README instructions + gameplay GIF. | /.github/workflows/ /scripts/core/events/ /data/lang/ /docs/QA_checklist.md | ☐
Month 9 (Weeks 33-36) | Networking basics, Behavior Trees AI, LevelLoader pipeline. | Boss AI + new overworld_v2 generated by loader. | /scripts/net/ /scripts/ai/behavior_tree/ /scripts/level_loader/ /scenes/overworld_v2/ | ☐
Month 10 (Weeks 37-40) | Profiling, Android/touch, analytics, architecture cleanup. | Alpha Build (15+ min gameplay) desktop + Android. | /scripts/debug/ProfilerOverlay.java /scripts/input/mobile/ /scripts/telemetry/ /README.md | ☐
Month 11 (Weeks 41-44) | Docs, trailer/screenshots, CV, Core Java/OOP interview prep. | Portfolio page draft + CV_draft.md + interview_core_java.md. | /docs/architecture.md /assets/marketing/ /docs/CV_draft.md /docs/interview_core_java.md | ☐
Month 12 (Weeks 45-52) | DSA/gameplay interview prep, team process, RC polish, applications. | Portfolio Ready Build + internship applications sent. | /builds/rc/ /docs/dev_process.md /docs/applications_tracker.xlsx /docs/next_steps_3mo.md | ☐